## Ark1
		Lofthus frukt og saft

		Employment and project planning					Research and planning					Design					Build website					Final testing					Launch website and bugfix
		01/08/18	02/08/18	03/08/18	04/08/18	05/08/18		08/08/18	09/08/18	10/08/18	11/08/18	12/08/18		15/08/18	16/08/18	17/08/18	18/08/18	19/08/18		22/08/18	23/08/18	24/08/18	25/08/18	26/08/18		29/08/18	30/08/18	31/08/18	01/09/18	02/09/18		05/09/18	06/09/18	07/09/18	08/09/18	09/09/18
		Day 1	Day 2	Day 3	Day 4	Day 5		Day 6	Day 7	Day 8	Day 9	Day 10		Day 11	Day 12	Day 13	Day 14	Day 15		Day 16	Day 17	Day 18	Day 19	Day 20		Day 21	Day 22	Day 23	Day 24	Day 25		Day 26	Day 27	Day 28	Day 29	Day 30

Project manager		Project management and contact with Lofthus					Project management and contact with Lofthus					Project management and contact with Lofthus					Project management and contact with Lofthus					Project management and contact with Lofthus					Project management and contact with Lofthus

Project manager		Find potential photographer, content developer and designer.			Interviews and employment

Project manager		Identify goals and general project planning

Project manager		Initial meeting with customer					Update meeting with customer					Update meeting with customer					Update meeting with customer				Presentation of site to customer			Feedback meeting with customer			Final meeting with customer

Project manager Developers Designer							Research for design and content

Project manager Developers Designer							Strategic planning

Project manager Developers Designer							Content planning

Project manager Developers Designer							Site outline

Project manager Photographer Designer							Plan photoshoots

Content developer							Research for content, headings, slogans					Create articles and texts					Adjust and process articles and texts

Photographer							Photoshoots for website and editing of images					Adjusting images, final touches

Designer							Style tile		Graphical elements/logo

Front-End Developer							Inspiration and planning		Initial coding				Coding and building site					Coding and building site

Developer Designer							UX testing/adjustments					UX testing/adjustments

Front-End Developer							Testing across platforms

Developer Designer Photographer							Refinement /final touch

Project manager Developer Designer							Launch!	Fixing bugs or petential issues